## Appendix A-3
APPENDIX A-3
LITTLE ROCK AGENCY TENDER (FORT WORTH AND KANSAS CITY) CROSSWALK PWS TASKS TO STAFFING-YEAR 3
PWS Para | PWS Para & Sub Task | TASK | POSITION & GRADE | (PWS WKLD) TASK COUNT | % PER TASK BY EACH POSITION | AVG. HOURS PER TASK | UNADJ. TOTAL REQ. HRS (1) | UNADJ. TOTAL FTE (2) | NOTES
4.1 | 4.1.1 | Vouchers Monthly |  | 8150 |  |  |  |  | Service will be provided by subcontract
4.1 | 4.1.2 | Vouchers- Special Claims |  | 556
4.1 | 4.1.2 | Process Special Claims | Financial Analyst GS-12 | 556 | 25% | 2 | 278 | 0.15653 | 25% split
4.1 | 4.1.2 | Process Special Claims | Financial Analyst GS-11 | 556 | 25% | 2 | 278 | 0.15653 | 25% split
4.1 | 4.1.2 | Process Special Claims | Financial Analyst GS-09 | 556 | 50% | 2 | 556 | 0.31306 | 50% split
4.2 | 4.2 | Management and Occupancy Reviews (MORs)
4.2 | 4.2 | Schedule, conduct, and complete an MOR report assessing owner/agent operations. |  | 1044 |  |  |  |  | See Note A.
4.2 | 4.2a | Create MOR work plan |  | 1044
4.2 | 4.2a | Create MOR work plan | Program Specialist GS-07 | 1044 | 80% |  | 80 | 0.045045 | Specialist GS-7 spends 80% of time on task. 100 hrs total for Work Plan.
4.2 | 4.2a | Create MOR work plan | Program Specialist GS-09 | 1044 | 20% |  | 20 | 0.011261 | Specialist GS-9 spends 20% of time on task.
4.2 | 4.2b | Conduct a desk review |  | 1044
4.2 | 4.2b | Conduct a desk review | Program Specialist GS-07 | 1044 | 80% | 2.5 | 2088 | 1.1757 | MEO Team Technical Estimate
4.2 | 4.2b | Conduct a desk review | Program Specialist GS-09 | 1044 | 20% | 2.5 | 522 | 0.29392 | MEO Team Technical Estimate
4.2 | 4.2c | Conduct an on-site review |  | 1044
4.2 | 4.2c | Conduct an on-site review | Program Specialist GS-07 | 1044 | 80% | 10.92 | 9120.384 | 5.1354 | Time standard specific for properties and area.
4.2 | 4.2c | Conduct an on-site review | Program Specialist GS-09 | 1044 | 20% | 10.92 | 2280.096 | 1.2838 | Time standard specific for properties and area.
4.2 | 4.2d | Conduct post-review activities |  | 1044
4.2 | 4.2d | Conduct post-review activities | Program Specialist GS-07 | 1044 | 80% | 4 | 3340.8 | 1.8811 | MEO Team Technical Estimate
4.2 | 4.2d | Conduct post-review activities | Program Specialist GS-09 | 1044 | 20% | 4 | 835.2 | 0.47027 | MEO Team Technical Estimate
4.3 | 4.3 | Renewal and Amendment of PRAC and PAC Contracts
4.3 | 4.3.1 | Prepare PRAC and PAC contract renewals |  | 147
4.3 | 4.3.1 | Prepare PRAC and PAC contract renewals | Prgm. Assistant (0303) GS-07 | 147 | 50% | 2.4 | 176.4 | 0.099324 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.1 | Prepare PRAC and PAC contract renewals | Prgm. Assistant (0303) GS-06 | 147 | 25% | 2.4 | 88.2 | 0.049662 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.1 | Prepare PRAC and PAC contract renewals | Prgm. Assistant (0303) GS-05 | 147 | 25% | 2.4 | 88.2 | 0.049662 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds needed |  | 170 |  |  |  |  | Figures reflect funds need 50% of the time.
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds needed | Prgm. Assistant (0303) GS-07 | 85 | 50% | 3.54 | 150.45 | 0.084713 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds needed | Prgm. Assistant (0303) GS-06 | 85 | 25% | 3.54 | 75.225 | 0.042356 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds needed | Prgm. Assistant (0303) GS-05 | 85 | 25% | 3.54 | 75.225 | 0.042356 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds are not needed |  | 170 |  |  |  |  | Figures reflect funds not needed 50% of the time.
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds are not needed | Prgm. Assistant (0303) GS-07 | 85 | 50% | 1.94 | 82.45 | 0.046425 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds are not needed | Prgm. Assistant (0303) GS-06 | 85 | 25% | 1.94 | 41.225 | 0.023212 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.3 | 4.3.2 | Prepare PRAC and PAC contract amendments when funds are not needed | Prgm. Assistant (0303) GS-05 | 85 | 25% | 1.94 | 41.225 | 0.023212 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.4 | 4.4 | Contract and other Rent Adjustments
4.4 | 4.4 | Process budget-based contact rent adjustments during the contract term in accordance with the contract and HUD requirements. |  | 157
4.4 | 4.4a | If the rent increase is approved |  | 157 | 85% |  |  |  | Figures reflect 85% approved
4.4 | 4.4a | If the rent increase is approved | Financial Analyst GS-12 | 133.45 | 25% | 4.49 | 149.7976 | 0.084346 | 25% split
4.4 | 4.4a | If the rent increase is approved | Financial Analyst GS-11 | 133.45 | 25% | 4.49 | 149.7976 | 0.084346 | 25% split
4.4 | 4.4a | If the rent increase is approved | Financial Analyst GS-09 | 133.45 | 50% | 4.49 | 299.5952 | 0.16869 | 50% split
4.4 | 4.4b | If rent increased is denied |  | 157 | 15% |  |  |  | Figures reflect 15% denied
4.4 | 4.4b | If rent increased is denied | Financial Analyst GS-12 | 23.55 | 25% | 5.18 | 30.4972 | 0.017172 | 25% split
4.4 | 4.4b | If rent increased is denied | Financial Analyst GS-11 | 23.55 | 25% | 5.18 | 30.4972 | 0.017172 | 25% split
4.4 | 4.4b | If rent increased is denied | Financial Analyst GS-09 | 23.55 | 50% | 5.18 | 60.9945 | 0.034344 | 50% split
4.5 | 4.5 | Health and Safety Issues or Community/Resident Concerns |  | 28
4.5 | 4.5.1 | Respond to all life threatening health and safety issues. | Prgm. Assistant (0303) GS-07 | 28 | 50% | 2 | 28 | 0.015766 | Activity split 50% to GS-06 and 07
4.5 | 4.5.1 | Respond to all life threatening health and safety issues. | Prgm. Assistant (0303) GS-06 | 28 | 50% | 2 | 28 | 0.015766 | Activity split 50% to GS-06 and 08
4.5 | 4.5.2 | Respond to all non-life threatening health and safety and community/resident concerns. |  | 1040
4.5 | 4.5.2 | Respond to all non-life threatening health and safety and community/resident concerns. | Prgm. Assistant (0303) GS-07 | 1040 | 50% | 0.75 | 390 | 0.21959 | MEO Team Technical Estimate
4.5 | 4.5.2 | Respond to all non-life threatening health and safety and community/resident concerns. | Prgm. Assistant (0303) GS-06 | 1040 | 50% | 0.75 | 390 | 0.21959 | MEO Team Technical Estimate
4.5 | 4.5.3 | Respond to all inquiries from Federal, State, or local governments. | Prgm. Assistant (0303) GS-07 | 28 | 100% | 2 | 56 | 0.031532 | MEO Team Technical Estimate
4.5 | 4.5.3 | Respond to all inquiries from Federal, State, or local governments. | Supervisory, Quality Control Analyst GS-14 | 28 | 100% | 1 | 28 | 0.015766 | Senior involvement required. MEO Team TE.
4.6 | 4.6 | Physical Inspection
4.6 | 4.6 | Follow-up on Physical Inspection. |  | 225
4.6 | 4.6a | Physical inspection related to EH&S issues | Prgm. Assistant (0303) GS-07 | 225 | 50% | 2.06 | 231.75 | 0.13049 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.6 | 4.6a | Physical inspection related to EH&S issues | Prgm. Assistant (0303) GS-06 | 225 | 25% | 2.06 | 115.875 | 0.065245 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.6 | 4.6a | Physical inspection related to EH&S issues | Prgm. Assistant (0303) GS-05 | 225 | 25% | 2.06 | 115.875 | 0.065245 | Divided 50% (GS-07); 25% (GS-06 & 05 each)
4.6 | 4.6b | Physical inspection related to substandard properties |  | 225 | 10% |  |  |  | 10% of all properties fall into this category
4.6 | 4.6b | Physical inspection related to substandard properties | Financial Analyst GS-12 | 22.5 | 50% | 4.2 | 47.25 | 0.026605 | Requires higher graded due to issues; divided 50% GS-12, 25% GS-11; and 25% GS-09
4.6 | 4.6b | Physical inspection related to substandard properties | Financial Analyst GS-11 | 22.5 | 25% | 4.2 | 23.625 | 0.013302 | Requires higher graded due to issues; divided 50% GS-12, 25% GS-11; and 25% GS-10
4.6 | 4.6b | Physical inspection related to substandard properties | Financial Analyst GS-09 | 22.5 | 25% | 4.2 | 23.625 | 0.013302 | Requires higher graded due to issues; divided 50% GS-12, 25% GS-11; and 25% GS-11
4.7 | 4.7 | Reporting Requirements
4.7 | 4.7.1 | Prepare an annual Work Plan. |  | 1 |  |  |  |  | Using MEO Team Tech Estimate
4.7 | 4.7.1 | Prepare an annual Work Plan. | Management Analyst (Info Systems) GS-12/13 | 1 | 100% |  | 20 | 0.011261
4.7 | 4.7.1 | Prepare an annual Work Plan. | Supervisory, Quality Control Analyst GS-14 | 1 | 100% |  | 20 | 0.011261
4.7 | 4.7.1 | Prepare an annual Work Plan. | Program Manager GS-14 | 1 | 100% |  | 20 | 0.011261
4.7 | 4.7.1 | Prepare an annual Work Plan. | Quality Control Analyst GS-12/13 | 1 | 100% |  | 30 | 0.016892
4.7 | 4.7.1 | Prepare an annual Work Plan. | Supervisory Financial Analyst GS-13 | 1 | 100% |  | 30 | 0.016892
4.7 | 4.7.1 | Prepare an annual Work Plan. | Supervisory Program Specialist GS-11 | 1 | 100% |  | 40 | 0.022523
4.7 | 4.7.1 | Prepare an annual Work Plan. | Financial Analyst GS-12 | 1 | 100% |  | 20 | 0.011261
4.7 | 4.7.1 | Prepare an annual Work Plan. | Prgm. Assistant (0303) GS-06 | 1 | 100% |  | 20 | 0.011261
4.7 | 4.7.2 | Submit to HUD a monthly report detailing accomplishments/activities and tracking logs for each requirement for the prior month with the monthly invoice. |  | 12 |  |  |  |  | Note: Used figure of 2.85 hours per report and multiplied by 12 reports. Data from survey.
4.7 | 4.7.2 | Submit to HUD a monthly report | Management Analyst (Info Systems) GS-12/13 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.2 | Submit to HUD a monthly report | Supervisory, Quality Control Analyst GS-14 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.2 | Submit to HUD a monthly report | Program Manager GS-14 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.2 | Submit to HUD a monthly report | Quality Control Analyst GS-12/13 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.2 | Submit to HUD a monthly report | Supervisory Financial Analyst GS-13 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.2 | Submit to HUD a monthly report | Supervisory Program Specialist GS-11 | 12 | 100% | 5.7 | 68.4 | 0.038514
4.7 | 4.7.2 | Submit to HUD a monthly report | Financial Analyst GS-12 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.2 | Submit to HUD a monthly report | Prgm. Assistant (0303) GS-06 | 12 | 100% | 2.85 | 34.2 | 0.019257
4.7 | 4.7.3 | HUD an annual Year-end Report. |  | 1 |  |  | 0 | 0%
4.7 | 4.7.3 | HUD an annual Year-end Report. | Management Analyst (Info Systems) GS-12/13 | 1 | 100% | 20 | 20 | 0.011261
4.7 | 4.7.3 | HUD an annual Year-end Report. | Supervisory, Quality Control Analyst GS-14 | 1 | 100% | 20 | 20 | 0.011261
4.7 | 4.7.3 | HUD an annual Year-end Report. | Program Manager GS-14 | 1 | 100% | 25 | 25 | 0.014077
4.7 | 4.7.3 | HUD an annual Year-end Report. | Quality Control Analyst GS-12/13 | 1 | 100% | 20 | 20 | 0.011261
4.7 | 4.7.3 | HUD an annual Year-end Report. | Supervisory Financial Analyst GS-13 | 1 | 100% | 10 | 10 | 0.0056306
4.7 | 4.7.3 | HUD an annual Year-end Report. | Supervisory Program Specialist GS-11 | 1 | 100% | 20 | 20 | 0.011261
4.7 | 4.7.3 | HUD an annual Year-end Report. | Financial Analyst GS-12 | 1 | 100% | 10 | 10 | 0.0056306
4.7 | 4.7.3 | HUD an annual Year-end Report. | Prgm. Assistant (0303) GS-06 | 1 | 100% | 10 | 10 | 0.0056306
4.8 | 4.8 | Appeals
4.8 | 4.8 | Process owner appeals of Service Provider decisions. |  | 28
4.8 | 4.8 | Process owner appeals of Service Provider decisions. | Program Specialist GS-09 | 28 | 20% | 11.73 | 65.688 | 0.036986
4.8 | 4.8 | Process owner appeals of Service Provider decisions. | Financial Analyst GS-11 | 28 | 20% | 11.73 | 65.688 | 0.036986
4.8 | 4.8 | Process owner appeals of Service Provider decisions. | Financial Analyst GS-12 | 28 | 40% | 11.73 | 131.376 | 0.073973
4.8 | 4.8 | Process owner appeals of Service Provider decisions. | Supervisory Financial Analyst GS-13 | 28 | 20% | 11.73 | 65.688 | 0.036986
4.9 | 4.9 | Waivers
4.9 | 4.9 | Receive and analyze waiver requests and provide recommendations to HUD for action. |  | 19
4.9 | 4.9 | Receive and analyze waiver requests and provide recommendations to HUD for action. | Supervisory Financial Analyst GS-13 | 19 | 100% | 2.9 | 55.1 | 0.031025
4.10 | 4.10 | Review Annual Audited Financial Statements
4.10 | 4.10.1 | Resolve compliance finding as reported as MF compliance issues by the REAC FASS-MF in accordance with HUD directives. |  | 260
4.10 | 4.10.2 | Conduct a complete review of all audited financial statements in accordance with HUD directives. |  | 1017
4.10 | 4.10.2 | Perform a complete review |  | 1017
4.10 | 4.10.2 | Perform a complete review | Financial Analyst GS-09 | 1017 | 25% | 4.72 | 1200.06 | 0.67571 | Financial Analyst GS-9 spends 25% of time on task.
4.10 | 4.10.2 | Perform a complete review | Financial Analyst GS-11 | 1017 | 25% | 4.72 | 1200.06 | 0.67571 | Financial Analyst GS-11 spends 25% of time on task.
4.10 | 4.10.2 | Perform a complete review | Financial Analyst GS-12 | 1017 | 50% | 4.72 | 2400.12 | 1.3514 | Financial Analyst GS-12 spends 50% of time on task.
4.10 | 4.10.2 | Follow-up after complete review |  | 1017 | 25% |  |  |  | Follow-up percentage = 25% based on historical rates
4.10 | 4.10.2 | Follow-up after complete review | Financial Analyst GS-09 | 254.25 | 25% | 2.4 | 152.55 | 0.085895 | Task divided 25% GS-09; 25% GS-11; and 50% GS-12
4.10 | 4.10.2 | Follow-up after complete review | Financial Analyst GS-11 | 254.25 | 25% | 2.4 | 152.55 | 0.085895 | Task divided 25% GS-09; 25% GS-11; and 50% GS-12
4.10 | 4.10.2 | Follow-up after complete review | Financial Analyst GS-12 | 254.25 | 50% | 2.4 | 305.1 | 0.17179 | Task divided 25% GS-09; 25% GS-11; and 50% GS-12
4.10 | 4.10.1 | Resolve Compliance Findings |  | 260 | 100%
4.10 | 4.10.1 | Resolve Compliance Findings | Financial Analyst GS-09 | 260 | 25% | 3.28 | 213.2 | 0.12005 | Financial Analyst GS-9 spends 25% of time on task.
4.10 | 4.10.1 | Resolve Compliance Findings | Financial Analyst GS-11 | 260 | 25% | 3.28 | 213.2 | 0.12005 | Financial Analyst GS-11 spends 25% of time on task.
4.10 | 4.10.1 | Resolve Compliance Findings | Financial Analyst GS-12 | 260 | 50% | 3.28 | 426.4 | 0.24009 | Financial Analyst GS-12 spends 50% of time on task.
4.10 | 4.10.1 | Follow-up with compliance findings if enforcement action required |  | 260 | 5% |  |  |  | Figures reflect enforcement follow-up 5% of the time.
4.10 | 4.10.1 | Follow-up with compliance findings if enforcement action required | Supervisory Financial Analyst GS-13 | 13 | 75% | 2.82 | 27.495 | 0.015481 | Supervisory, Financial Analyst GS-13 spends 75% of total time on task.
4.10 | 4.10.1 | Follow-up with compliance findings if enforcement action required | Financial Analyst GS-12 | 13 | 25% | 2.82 | 9.165 | 0.0051605 | Financial Analyst GS-12 spends 25% of total time on task.
4.11 | 4.11 | Monthly Accounting Reports (MARs)
4.11 | 4.11 | Request and review MARs using HUD forms 93479, Report for Establishing Net Income; 93480, Schedule of Disbursements; and 93481, Schedule of Accounts. |  | 65
4.11 | 4.11a | Planning to obtain MARs |  | 65 |  |  |  |  | One time annually.
4.11 | 4.11a | Planning to obtain MARs | Prgm. Assistant (0303) GS-07 | 65 | 100% | 1.62 | 105.3 | 0.059291
4.11 | 4.11b | Review the reports with follow-up |  | 780 |  |  |  |  | The number of reports is based on the number of properties multiplied by 12.
4.11 | 4.11b | Review the reports with follow-up | Financial Analyst GS-09 | 780 | 50% | 0.56 | 218.4 | 0.12297 | Technical Estimate based on 75% of MARs not requiring follow-up and 25% requiring follow-up of some sorts. This is a weighted average.
4.11 | 4.11b | Review the reports with follow-up | Financial Analyst GS-11 | 780 | 25% | 0.56 | 109.2 | 0.061486 | See above
4.11 | 4.11b | Review the reports with follow-up | Financial Analyst GS-12 | 780 | 25% | 0.56 | 109.2 | 0.061486 | See above
4.12 | 4.12 | Management Certifications
4.12 | 4.12 | Process Management Certifications. |  | 70
4.12 | 4.12a | Review and receipt of management certificates |  | 70 | 100%
4.12 | 4.12a | Review and receipt of management certificates | Prgm. Assistant (0303) GS-07 | 70 | 90% | 1.81 | 114.03 | 0.064206
4.12 | 4.12a | Review and receipt of management certificates | Financial Analyst GS-11 | 70 | 5% | 1.81 | 6.335 | 0.003567 | Periodic oversight and expert intervention required
4.12 | 4.12a | Review and receipt of management certificates | Financial Analyst GS-12 | 70 | 5% | 1.81 | 6.335 | 0.003567 | Periodic oversight and expert intervention required
4.12 | 4.12b | Follow-up with disapproved management certificates |  | 70 | 25% |  |  |  | Figures reflect follow-up activity occurring 25% of time.
4.12 | 4.12b | Follow-up with disapproved management certificates | Financial Analyst GS-11 | 17.5 | 50% | 1.7 | 14.875 | 0.0083756 | Time split evenly among GS-11 & GS-12
4.12 | 4.12b | Follow-up with disapproved management certificates | Financial Analyst GS-12 | 17.5 | 50% | 1.7 | 14.875 | 0.0083756 | Time split evenly among GS-11 & GS-13
4.13 | 4.13 | HUD 2530 Previous Participation Certifications
4.13 | 4.13 | Process HUD 2530, Previous Participation Certification Form in accordance with HUD directives. |  | 70
4.13 | 4.13a | Tracking, verifying, and explaining HUD 2530s | Prgm. Assistant (0303) GS-07 | 70 | 50% | 2.42 | 84.7 | 0.047691
4.13 | 4.13a | Tracking, verifying, and explaining HUD 2530s | Prgm. Assistant (0303) GS-06 | 70 | 25% | 2.42 | 42.35 | 0.023846
4.13 | 4.13a | Tracking, verifying, and explaining HUD 2530s | Prgm. Assistant (0303) GS-05 | 70 | 25% | 2.42 | 42.35 | 0.023846
4.14 | 4.14 | Excess Income Reports
4.14 | 4.14 | Process Section 236 Excess Income Reports in accordance with HUD directives. |  | 314
4.14 | 4.14.2 | Process owner's requests to retain excess income in accordance with HUD directives. | Financial Analyst GS-09 | 11 | 100% | 1.02 | 11.22 | 0.0063176 | MEO Team Technical Estimate
4.14 | 4.14.3 | Cure excess income delinquencies in accordance with HUD directives. | Financial Analyst GS-09 | 6 | 100% | 1.02 | 6.12 | 0.0034459 | MEO Team Technical Estimate
4.14 | 4.14.1 | Review excess income reports monthly |  | 314
4.14 | 4.14.1 | Review excess income reports monthly | Prgm. Assistant (0303) GS-07 | 314 | 80% | 1.02 | 256.224 | 0.14427 | Split 80% Program Assistant and 20% Fin. Analyst
4.14 | 4.14.1 | Review excess income reports monthly | Financial Analyst GS-09 | 314 | 10% | 1.02 | 32.028 | 0.018034 | 20% for Fin. Analysts split among 3 grades
4.14 | 4.14.1 | Review excess income reports monthly | Financial Analyst GS-11 | 314 | 5% | 1.02 | 16.014 | 0.0090169 | 20% for Fin. Analysts split among 3 grades
4.14 | 4.14.1 | Review excess income reports monthly | Financial Analyst GS-12 | 314 | 5% | 1.02 | 16.014 | 0.0090169 | 20% for Fin. Analysts split among 3 grades
4.14 | 4.14.1 | Review excess income reports yearly |  | 314
4.14 | 4.14.1 | Review excess income reports yearly | Financial Analyst GS-09 | 314 | 25% | 1.56 | 122.46 | 0.068953 | Financial Analyst GS-9 spends 25% of time on task.
4.14 | 4.14.1 | Review excess income reports yearly | Financial Analyst GS-11 | 314 | 25% | 1.56 | 122.46 | 0.068953 | Financial Analyst GS-11 spends 25% of time on task.
4.14 | 4.14.1 | Review excess income reports yearly | Financial Analyst GS-12 | 314 | 50% | 1.56 | 244.92 | 0.13791 | Financial Analyst GS-12 spends 50% of time on task.
4.15 | 4.15 | Residual Receipts
4.15 | 4.15 | Monitor and process all requests for releases from the Residual Receipts Account in accordance with HUD directives. |  | 170
4.15 | 4.15a | Residual Receipts |  | 170 | 100%
4.15 | 4.15a | Residual Receipts | Prgm. Assistant (0303) GS-07 | 170 | 80% | 1.21 | 164.56 | 0.092658 | Program Assistant GS-7 will perform 80% of tasks
4.15 | 4.15a | Residual Receipts | Financial Analyst GS-09 | 170 | 5% | 1.21 | 10.285 | 0.0057911 | Financial Analyst GS-09 spends 5% of time on task.
4.15 | 4.15a | Residual Receipts | Financial Analyst GS-11 | 170 | 10% | 1.21 | 20.57 | 0.011582 | Financial Analyst GS-11 spends 10% of time on task.
4.15 | 4.15a | Residual Receipts | Financial Analyst GS-12 | 170 | 5% | 1.21 | 10.285 | 0.0057911 | Financial Analyst GS-12 spends 5% of time on task.
4.16 | 4.16 | Reserve for Replacement
4.16 | 4.16 | Monitor and process Reserve for Replacement activity in accordance with HUD directives. |  | 1125
4.16 | 4.16a | Reserve for Replacement |  | 1125 | 100%
4.16 | 4.16a | Reserve for Replacement | Prgm. Assistant (0303) GS-07 | 1125 | 80% | 1.53 | 1377 | 0.77534 | Program Assistant GS-7 will perform 80% of tasks
4.16 | 4.16a | Reserve for Replacement | Financial Analyst GS-09 | 1125 | 5% | 1.53 | 86.0625 | 0.048459 | Financial Analyst GS-09 spends 5% of time on task.
4.16 | 4.16a | Reserve for Replacement | Financial Analyst GS-11 | 1125 | 10% | 1.53 | 172.125 | 0.096917 | Financial Analyst GS-11 spends 10% of time on task.
4.16 | 4.16a | Reserve for Replacement | Financial Analyst GS-12 | 1125 | 5% | 1.53 | 86.0625 | 0.048459 | Financial Analyst GS-12 spends 5% of time on task.
4.17 | 4.17 | Service Coordinator
4.17 | 4.17 | Monitor and review all requests for Service Coordinator activity in accordance with HUD directives. |  | 95
4.17 | 4.17a | Process vouchers |  | 380 |  |  |  |  | Number of vouchers estimated at quarterly since owner may submit throughout the year and the PWS number is assumed to refer to SC contracts.
4.17 | 4.17a | Process vouchers | Financial Analyst GS-09 | 380 | 25% | 1 | 95 | 0.053491 | MEO Team Technical Estimate
4.17 | 4.17a | Process vouchers | Financial Analyst GS-11 | 380 | 50% | 1 | 190 | 0.10698 | MEO Team Technical Estimate
4.17 | 4.17a | Process vouchers | Financial Analyst GS-12 | 380 | 25% | 1 | 95 | 0.053491 | MEO Team Technical Estimate
4.17 | 4.17b | Renew grants |  | 95 | 100%
4.17 | 4.17b | Renew grants | Financial Analyst GS-09 | 95 | 25% | 2.34 | 55.575 | 0.031292 | Financial Analyst GS-9 spends 25% of time on task.
4.17 | 4.17b | Renew grants | Financial Analyst GS-11 | 95 | 50% | 2.34 | 111.15 | 0.062584 | Financial Analyst GS-11 spends 25% of time on task.
4.17 | 4.17b | Renew grants | Financial Analyst GS-12 | 95 | 25% | 2.34 | 55.575 | 0.031292 | Financial Analyst GS-12 spends 50% of time on task.
4.17 | 4.17c | Review semi-annual performance reports and semi-annual financial status reports |  | 190 | 100% |  |  |  | 95 times 2 because semi-annual - change workload indicator.
4.17 | 4.17c | Review semi-annual performance reports and semi-annual financial status reports | Financial Analyst GS-09 | 190 | 50% | 1.32 | 125.4 | 0.070608 | Financial Analyst GS-9 spends 25% of time on task.
4.17 | 4.17c | Review semi-annual performance reports and semi-annual financial status reports | Financial Analyst GS-11 | 190 | 25% | 1.32 | 62.7 | 0.035304 | Financial Analyst GS-11 spends 25% of time on task.
4.17 | 4.17c | Review semi-annual performance reports and semi-annual financial status reports | Financial Analyst GS-12 | 190 | 25% | 1.32 | 62.7 | 0.035304 | Financial Analyst GS-12 spends 50% of time on task.
4.17 | 4.17d | Review semi-annual financial status reports |  | 190 |  |  |  |  | 95 times 2 because semi-annual - change workload indicator.
4.17 | 4.17d | Review semi-annual financial status reports | Financial Analyst GS-09 | 190 | 50% | 1.74 | 165.3 | 0.093074
4.17 | 4.17d | Review semi-annual financial status reports | Financial Analyst GS-11 | 190 | 25% | 1.74 | 82.65 | 0.046537
4.17 | 4.17d | Review semi-annual financial status reports | Financial Analyst GS-12 | 190 | 25% | 1.74 | 82.65 | 0.046537
4.17 | 4.17e | Process budget-based rent increases |  | 95 |  |  |  |  | Rent increases are included in 5.4 contract and other Rent Adjustments. The MEO Team did not want to double count this sub-group of total rent increases.
4.18 | 4.18 | Use Agreements
4.18 | 4.18 | Schedule, conduct, and complete a Compliance Review report assessing owner/agent compliance with all agreement requirements |  | 609 |  |  |  |  | See Note 3.
4.18 | 4.18 | Schedule, conduct, and complete a Compliance Review report assessing owner/agent compliance with all agreements. The Compliance Review is conducted as part of an MOR. (No separate travel required) | Program Specialist GS-07 | 181 | 100% | 1.03 | 186.43 | 0.10497 | Travel for these Compliance Reviews is already captured in the analysis for MOR travel. Consequently, the technical estimate only reflects the review time and follow-up time for a single Compliance Review.
4.18 | 4.18 | Schedule, conduct, and complete a Compliance Review report assessing owner/agent compliance with all agreement requirements with separate Travel Required | Program Specialist GS-07 | 428 | 100% | 3.81 | 1630.68 | 0.91818 | Separate travel will be required for this set of Use Agreement properties. The technical estimate is based on 1.03 hours for the actual Compliance Review, plus an average weighted travel time specifically developed based on the properties in the service area.
|  | TOTAL |  |  |  |  | 36365.6695 | 20.4762
Note A: Workload, per direction of the Contracting Officer reply 9/28/05, is taken from the PWS MOR count in the C-4 Workload Tables. The MEO Team did not vary any work counts. This leads to a revision to MEO staffing and work counts used above.
(1) Determined by multiplying time per task by the workload indicator for raw required hours.
(2) Divides raw, unadjusted hours by the A-76 required 1,776 hours to equate to FTEs.
(3) The number of properties requiring use agreement reviews (Compliance Reviews) is based on Amendment 5 Appendices H and I. The MEO Team performed an analysis to determine which properties could be covered in tandem with MOR on-site reviews and which properties would require separate visits to meet the PWS requirements. The two numbers in the count column area a result of this analysis. Taken together, they represent the total number of Compliance Reviews performed by the MEO for this performance period. Those properties covered by PBCA, as directed in Question and Answer 224 issued 6/28 Amendment 5, are excluded from this count.

## Appendix B-3
APPENDIX B-3
ADJUSTED HOURS, FTE & MEO FOR FTW & KC AREA AGENCY TENDER - YEAR 3
Position Title and Grade and Division | Unadjusted Hours | Supervisory Hours (4) | Quality Control Hours (5) | HR & Info Tech Hours (6) | Meetings (2) | Training (3) | Breaks (1) | Unadjusted Total (7) | Unadjusted FTE (8) | Adjusted FTE (9) | Location of Staff
Director's Office
Program Manager GS-14 | #VALUE! | 1500 |  |  | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Supervisory, QC Control Analyst/Deputy Program Manager GS-13/14 | #VALUE! | 850 | 600 |  | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Quality Control Analyst GS-12/13 | #VALUE! | 0 | 1500 |  | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Management Analyst (Info Systems) GS-12/13 | #VALUE! | 0 |  | 1500 | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Administrative Specialist GS-11 | 0 | 0 |  | 800 | 15 | 29.625 | 52.7891 | 897.4141 | 0.5053 | 0.75 | LITTLE ROCK
Program Compliance & Monitoring Division
Supervisory Program Specialist GS-11 | #VALUE! | 1250 | 200 |  | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Program Specialist GS-09 | #VALUE! | 0 |  |  | 60 | 118.5 | #VALUE! | #VALUE! | #VALUE! | 3 | Outstationed
Program Specialist GS-07 | #VALUE! | 0 |  |  | 220 | 434.5 | #VALUE! | #VALUE! | #VALUE! | 11 | Outstationed
Program Assistant GS-06 | 0 | 0 |  | 1300 | 20 | 39.5 | 84.9688 | 1444.4688 | 0.81333 | 1 | LITTLE ROCK
Financial Processing Division
Supervisory Financial Analyst GS-13 | #VALUE! | 1200 | 150 |  | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Financial Analyst GS-12 | #VALUE! | 0 |  |  | 60 | 118.5 | #VALUE! | #VALUE! | #VALUE! | 3 | LITTLE ROCK
Financial Analyst GS-11 | #VALUE! | 0 |  |  | 40 | 79 | #VALUE! | #VALUE! | #VALUE! | 2 | LITTLE ROCK
Financial Analyst GS-09 | #VALUE! | 0 |  |  | 40 | 79 | #VALUE! | #VALUE! | #VALUE! | 2 | LITTLE ROCK
Program Assistant GS-07 | #VALUE! | 0 |  |  | 40 | 79 | #VALUE! | #VALUE! | #VALUE! | 2 | LITTLE ROCK
Program Assistant GS-06 | #VALUE! | 0 |  |  | 20 | 39.5 | #VALUE! | #VALUE! | #VALUE! | 1 | LITTLE ROCK
Program Assistant GS-05 | #VALUE! | 0 |  |  | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | LITTLE ROCK
TOTAL | #VALUE! | 4800 | 2450 | 3600 | 635 | 1254.125 | #VALUE! | #VALUE! | #VALUE! | 31.75
(1) Based on 111 hours of breaks for 222 federal work days. | [8 empty] | Total Available Hours (10) | 56388
(2) Based on 20 hours per year.
(3) Based on 39.5 actual training hrs per FTE per year
(4) Required to create a management infrastructure per PWS requirements.
(5) Required to create a quality control infrastructure per PWS requirements.
(6) Hours for Human Resources and Information Technology positions, as general administrative work.
(7) Unadjusted total hours equals PWS driven hours plus breaks, training, supervisory, quality control, administrative activities, and meetings.
(8) 1776 hours per FTE.
(9) Creates full positions to actually staff the MEO
(10) This equates to total hours to perform all PWS and associated work.
Position Title and Grade and Division | Adjusted FTE | Location of Staff
Director's Office
Program Manager GS-14 | 1 | LITTLE ROCK
Supervisory, QC Control Analyst/Deputy Program Manager GS-13/14 | 1 | LITTLE ROCK
Quality Control Analyst GS-12/13 | 1 | LITTLE ROCK
Management Analyst (Info Systems) GS-12/13 | 1 | LITTLE ROCK
Administrative Specialist GS-11 | 0.75 | LITTLE ROCK
Program Compliance & Monitoring Division
Supervisory Program Specialist GS-11 | 1 | LITTLE ROCK
Program Specialist GS-09 | 3 | Outstationed
Program Specialist GS-07 | 11 | Outstationed
Program Assistant GS-06 | 1 | LITTLE ROCK
Financial Processing Division
Supervisory Financial Analyst GS-13 | 1 | LITTLE ROCK
Financial Analyst GS-12 | 3 | LITTLE ROCK
Financial Analyst GS-11 | 2 | LITTLE ROCK
Financial Analyst GS-09 | 2 | LITTLE ROCK
Program Assistant GS-07 | 2 | LITTLE ROCK
Program Assistant GS-06 | 1 | LITTLE ROCK
TOTAL | 31.75

## Appendix C-3
APPENDIX C-3
UNADJUSTED HOURS BY PWS TASK AND MEO POSITION - YEAR 3
Sum of UNADJ. TOTAL REQ. HRS (1) | PWS Para
POSITION & GRADE | 4.1 | 4.11 | 4.12 | 4.13 | 4.14 | 4.15 | 4.16 | 4.17 | 4.18 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6 | 4.7 | 4.8 | 4.9 | 4.10 | Grand Total
(blank) | PWS Para 4.7: 0 | 0
Financial Analyst GS-09 | PWS Para 4.1: 556; PWS Para 4.11: 218.4; PWS Para 4.14: 171.828; PWS Para 4.15: 10.285; PWS Para 4.16: 86.0625; PWS Para 4.17: 441.275; PWS Para 4.4: 360.5897; PWS Para 4.6: 23.625; PWS Para 4.10: 1565.81 | 3433.8753
Financial Analyst GS-11 | 278 | 109.2 | 21.21 |  | 138.474 | 20.57 | 172.125 | 446.5 |  |  |  | 180.2949 |  | 23.625 |  | 65.688 |  | 1565.81 | 3021.4969
Financial Analyst GS-12 | 278 | 109.2 | 21.21 |  | 260.934 | 10.285 | 86.0625 | 295.925 |  |  |  | 180.2949 |  | 47.25 | 64.2 | 131.376 |  | 3140.785 | 4625.5224
Prgm. Assistant (0303) GS-05 | PWS Para 4.13: 42.35; PWS Para 4.3: 204.65; PWS Para 4.6: 115.875 | 362.875
Prgm. Assistant (0303) GS-06 | PWS Para 4.13: 42.35; PWS Para 4.3: 204.65; PWS Para 4.5: 418; PWS Para 4.6: 115.875; PWS Para 4.7: 64.2 | 845.075
Prgm. Assistant (0303) GS-07 | PWS Para 4.11: 105.3; PWS Para 4.12: 114.03; PWS Para 4.13: 84.7; PWS Para 4.14: 256.224; PWS Para 4.15: 164.56; PWS Para 4.16: 1377; PWS Para 4.3: 409.3; PWS Para 4.5: 474; PWS Para 4.6: 231.75 | 3216.864
Program Manager GS-14 | PWS Para 4.7: 79.2 | 79.2
Program Specialist GS-07 | PWS Para 4.18: 1817.11; PWS Para 4.2: 14629.184 | 16446.294
Program Specialist GS-09 | PWS Para 4.2: 3657.296; PWS Para 4.8: 65.688 | 3722.984
Supervisory Financial Analyst GS-13 | PWS Para 4.7: 74.2; PWS Para 4.8: 65.688; PWS Para 4.9: 55.1; PWS Para 4.10: 27.495 | 222.483
Supervisory Program Specialist GS-11 | PWS Para 4.7: 128.4 | 128.4
Supervisory, Quality Control Analyst GS-14 | PWS Para 4.5: 28; PWS Para 4.7: 74.2 | 102.2
Management Analyst (Info Systems) GS-12/13 | PWS Para 4.7: 74.2 | 74.2
Quality Control Analyst GS-12/13 | PWS Para 4.7: 84.2 | 84.2
Grand Total | 1112 | 542.1 | 156.45 | 169.4 | 827.46 | 205.7 | 1721.25 | 1183.7 | 1817.11 | 18286.48 | 818.6 | 721.1795 | 920 | 558 | 642.8 | 328.44 | 55.1 | 6299.9 | 36365.6695

## PWS Task to Hours
Sum of UNADJ. TOTAL REQ. HRS (1)
PWS Para | Total
4.1 | 1112 | 0.62613
4.11 | 542.1 | 0.30524
4.12 | 156.45 | 0.088091
4.13 | 169.4 | 0.095383
4.14 | 827.46 | 0.46591
4.15 | 205.7 | 0.11582
4.16 | 1721.25 | 0.96917
4.17 | 1183.7 | 0.6665
4.18 | 1817.11 | 1.0231
4.2 | 18286.48 | 10.2964
4.3 | 818.6 | 0.46092
4.4 | 721.1795 | 0.40607
4.5 | 920 | 0.51802
4.6 | 558 | 0.31419
4.7 | 642.8 | 0.36194
4.8 | 328.44 | 0.18493
4.9 | 55.1 | 0.031025
4.10 | 6299.9 | 3.5472
Grand Total | 36365.6695

## Unadjusted FTE
RAW UNADJUSTED FTE BY SUB LOCATION
Sum of UNADJ. TOTAL REQ. HRS (1)
POSITION & GRADE | Total
(blank) | 0 | 0
Financial Analyst GS-09 | 3433.8752 | 1.9335
Financial Analyst GS-11 | 3021.4969 | 1.7013
Financial Analyst GS-12 | 4625.5224 | 2.6045
Prgm. Assistant (0303) GS-05 | 362.875 | 0.20432
Prgm. Assistant (0303) GS-06 | 845.075 | 0.47583
Prgm. Assistant (0303) GS-07 | 3216.864 | 1.8113
Program Manager GS-14 | 79.2 | 0.044595
Program Specialist GS-07 | 16446.294 | 9.2603
Program Specialist GS-09 | 3722.984 | 2.0963
Supervisory Financial Analyst GS-13 | 222.483 | 0.12527
Supervisory Program Specialist GS-11 | 128.4 | 0.072297
Supervisory, Quality Control Analyst GS-14 | 102.2 | 0.057545
Management Analyst (Info Systems) GS-12/13 | 74.2 | 0.041779
Quality Control Analyst GS-12/13 | 84.2 | 0.04741
Grand Total | 36365.6695 | 20.4762